## Sheet1
House Scope: | Group Names
Size of House: 2,500sq ft | Emily Scharmann
Style: Bungalow | Maryia Spirydonava
Size of Land: 3 acres | Irek Scieszka
Bedrooms(3)
Bathroom(2.5) | Section Group 7
Cost to Build/Sell: $650,000
Start to Finish Duration: 7 months
Location: Essex, New York
Possible Extras: Fireplace, basement

## Sheet2
Foundation |  | Duration: | Start Date: | End Date: | Predecessor Tasks: | Resource Initials:
1.Subtask:Prepare site
| sub-subtask: Level site | 4 Days | 2016-05-01 | 2016-05-04 |  | ES, MS, IS
| sub-subtask: Put up wooden forms | 4 Days | 2016-05-05 | 2016-05-08 |  | ES, MS, IS
| sub-subtask: Dig holes and trenches | 6 Days | 2016-05-09 | 2016-05-14 |  | ES, MS, IS
2.Subtask: Pour foundation | sub-subtask: Form and pour footing | 2 Days | 2016-05-15 | 2016-05-16 | foundation subtask 1 | ES, MS, IS
| sub-subtask: Form and pour foundation | 2 Days | 2016-05-17 | 2016-05-18 | foundation subtask 1 | ES, MS, IS
| sub-subtask: Cure concrete | 4 Days | 2016-05-19 | 2016-05-22 | foundation subtask 1 | ES, MS, IS
3.Subtask: Installation | sub-subtask: Waterproof membrane of foundation walls | 2 Days | 2016-05-23 | 2016-05-24 | foundation subtask 1,2 | ES, MS, IS
| sub-subtask:Install drains, sewer, and water taps | 3 Days | 2016-05-25 | 2015-05-27 | foundation subtask 1,2 | ES, MS, IS
4. Subtask: Inspection | sub-subtask: City inspector | 2 Days | 2016-05-28 | 2016-05-29 | foundation subtask 1,2,3 | ES, MS, IS
Framing:
1. Subtask:Create Skeleton of House
| sub-subtask: Floor Systems | 2 Weeks | 2016-05-30 | 2016-06-12 | foundation | ES, MS, IS
| sub-subtask: Wall Systems | 2 Weeks | 2016-06-13 | 2016-06-27 | foundation | ES, MS, IS
| sub-subtask: Roof System | 2 Weeks | 2016-06-28 | 2016-07-12 | foundation | ES, MS, IS
2. Subtask: Sheathing
| sub-subtask: Plywood applied to exterior walls and roof | 5 Days | 2016-07-13 | 2016-07-17 | foundation | ES, MS, IS
| sub-subtask: Exterior Doors installed | 2 Days | 2016-07-18 | 2016-07-19 | foundation | ES, MS, IS
| sub-subtask: Windows installed | 2 Days | 2016-07-20 | 2016-07-21 | foundation | ES, MS, IS
| sub-subtask: House wrap applied | 3 Days | 2016-07-22 | 2016-07-24 | foundation | ES, MS, IS
3. Subtask: Inspection
Wiring
1. Subtask:Electrical Wiring | [5 empty] | ES, MS, IS
| sub-subtask: Run wires through interior walls, ceilings, and floors | 1 Week | 2016-07-25 | 2016-08-01 | foundation, framing | ES, MS, IS
| sub-subtask: Ductwork installation | 4 Days | 2016-08-02 | 2016-08-05 | foundation, framing | ES, MS, IS
| sub-subtask: HVAC pipes are installed through the roof | 3 Days | 2016-08-06 | 2015-08-08 | foundation, framing | ES, MS, IS
| sub-subtask: Install outlets, lights, switches, and run wires | 3 Days | 2016-08-09 | 2016-08-11 | foundation, framing | ES, MS, IS
| sub-subtask: Inspection | 2 Days | 2016-08-12 | 2016-08-13 | foundation, framing | ES, MS, IS
Plumbing:
1. Subtask: Installation
| sub-subtask: Sewer lines and vents are installed | 4 Days | 2016-08-14 | 2016-08-17 | foundation, framing | ES, MS, IS
| sub-subtask: Water supply lines | 5 Days | 2016-08-18 | 2016-08-22 | foundation, framing | ES, MS, IS
| sub-subtask: Bathtub installation | 2 Days | 2016-08-23 | 2016-08-24 | foundation, framing | ES, MS, IS
| sub-subtask: Inspection | 2 Days | 2016-08-25 | 2016-08-26 | foundation, framing | ES, MS, IS
Insullation:
1. Subtask: Installation
| sub-subtask: Exterior Walls | 4 Days | 2016-08-27 | 2016-08-30 | foundation, framing, wiring | ES, MS, IS
| sub-subtask: Attic | 4 Days | 2016-09-01 | 2016-09-04 | foundation, framing, wiring | ES, MS, IS
| sub-subtask: Basement | 4 Days | 2016-09-05 | 2016-09-09 | foundation, framing, wiring | ES, MS, IS
Drywall:
1. Subtask: Assembly
| sub-subtask: Hang and tape drywall | 3 Days | 910/16 | 2016-09-13 | foundation, framing, wiring, | ES, MS, IS
2.Subtask: Texturize Drywall | [5 empty] | ES, MS, IS
| sub-subtask: sand drywall | 2 Days | 2016-09-14 | 2016-09-16 | foundation, framing, wiring | ES, MS, IS
| sub-subtask: tape drywall | 2 Days | 2016-09-17 | 2016-09-19 | foundation, framing, wiring | ES, MS, IS
| sub-subtask: prime drywall | 2 Days | 2016-09-20 | 2016-09-22 | foundation, framing, wiring | ES, MS, IS
| sub-subtask: paint drywall | 2 Days | 2016-09-23 | 2016-09-25 | foundation, framing, wiring | ES, MS, IS
Interior:
Subtask: Install
| sub-subtask: Interior Door | 2 Days | 2016-09-26 | 2016-09-28 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Baseboards | 4 Days | 2016-09-29 | 2016-10-03 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Door Casings | 3 Days | 2016-10-04 | 2016-10-07 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Windowsill | 5 Days | 2016-10-08 | 2016-10-13 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Molding | 6 Days | 2016-10-14 | 2016-10-20 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Stair ballister | 6 Days | 2016-10-21 | 2016-10-27 | foundtion, framing, wiring, drywall | ES, MS, IS
ES, MS, IS
Subtask: Decorative Features | [5 empty] | ES, MS, IS
| sub-subtask:Cabinet Installation | 5 Days | 2016-10-28 | 2016-11-02 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask:Vanity Installation | 5 Days | 2016-11-03 | 2016-11-08 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask:Fireplace Installation | 3 Days | 2016-11-09 | 2016-11-12 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Install tile in bathrooms and kitchen | 8 Days | 2016-11-13 | 2016-11-21 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Paint walls | 9 Days | 2016-11-22 | 11/31/2016 | foundtion, framing, wiring, drywall | ES, MS, IS
Subtask: Flooring
| sub-subtask: Install ceramic flooring | 4 Days | 2016-12-01 | 2016-12-05 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Install Wood flooring | 4 Days | 2016-12-06 | 2016-12-10 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Finish Grading | 2 Days | 2016-12-11 | 2016-12-13 | foundtion, framing, wiring, drywall | ES, MS, IS
Subtask: Mechanical Trims
| sub-subtask: Install bathroom fixtures | 5 Days | 2016-12-14 | 2016-12-19 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: sinks, toilets and faucets | 6 Days | 2016-12-20 | 2016-12-26 | foundtion, framing, wiring, drywall | ES, MS, IS
| sub-subtask: Appliances are installed | 3 Days | 2016-12-27 | 2016-12-30 | foundtion, framing, wiring, drywall | ES, MS, IS
Exterior:
Subtask: Driveway and Walk-throughs
| sub-subtask: level area for driveway | 2 Days | 2016-12-31 | 2017-01-01 | completion of need for heavy equipment | ES, MS, IS
| sub-subtask: form area and pour cement | 4 Days | 2017-01-02 | 2017-01-06 | completion of need for heavy equipment | ES, MS, IS
| sub-subtask: let cement set | 4 Days | 2017-01-07 | 2017-01-11 | completion of need for heavy equipment | ES, MS, IS
Subtask: Landscaping
| sub-subtask: plant trees | 3 Days | 2017-01-12 | 2017-01-15 | completion of need for heavy equipment | ES, MS, IS
| sub-subtask: plant bushes | 3 Days | 2017-01-16 | 2017-01-19 | completion of need for heavy equipment | ES, MS, IS
| sub-subtask: plant flowers | 2 Days | 2017-01-20 | 2017-01-22 | completion of need for heavy equipment | ES, MS, IS
Final Inspection:
[5 empty] | completion of house | ES, MS, IS